## Accounts Tasks
RC | Accounts' Status
| Account | Lead | Status
| Globe | Yaniv | STOP (only up to 2 hrs work can be completed) Data Modelling required for Misaligned Component - MRF flow
| Sprint | Yaniv | STOP (only up to 2 hrs work can be completed)
| XLCom | Maya | STOP (only up to 2 hrs work can be completed) Wrong Charging, Quota Not Update - waiting for UTS-Krrish resolve, Unsync - needs remodeling per new format
| Cricket | Yaniv | STOP (only up to 2 hrs work can be completed)
| USCC | Yaniv | STOP (only up to 2 hrs work can be completed) Uploaded 2 dispatch flows
| TefArg | Maya | STOP (only up to 2 hrs work can be completed) Pending full classification by Rodrigo + Decision which flows to model - Ongoing
| Bell Canada | Maya | STOP (only up to 2 hrs work can be completed) "User ID / Password Issue" flow modelled - Waiting for Krrish and AO configurations on site
0.3 monthly | Airtel | Maya | High priority Deployed "Order Not Generated", Attachment config. For "Order Not Generated", Parsing - new atom for "NMS Release Scenario"
| Metro PCS | Maya | STOP (only up to 2 hrs work can be completed)
0.25 one time | TKS | Maya | To start
| Open Tasks - Non Dev | FP | Note
| Maya KT | Yaniv, Maya | Started going through the Amily web service code
| DevOps in Amily | Yaniv | On hold
| UTS querying service | Yaniv | A story was opened in Jira by Galit
| Cluster validation using partially labeld data applied on documents | Yaniv, Maya
Limitation to number of values parsed - Ask Bharati/Hetal

## Dashboard
| 38 | 1 | 2 | 14 | 6 | 6 | 8 | 0 | 0 | 0 | 6
| E2E Automation Flows | [5 empty] | Dispatch Flows |  |  |  |  | Date | Flows
Account Status | Prod. - Activated | Prod. - Deactivated | Labeling | Dev. | Dev. - Testing | Descoped | Prod. - Activated | Prod. - Deactivated | Dev. | Dev. - Testing | Descoped | 2017-08-01 | 0
Globe | 7 | 0 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 3 | 2017-08-02 | 0
Sprint | 11 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2017-08-03 | 0
XL Axiata | 4 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-04 | 0
Cricket | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 2017-08-05 | 0
USCC | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 2017-08-06 | 8
Bell Canada | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-07 | 8
Airtel | 5 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-08 | 8
Tef Argentina | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-09 | 8
MetroPCS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-10 | 8
Telkomsel | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-08-11 | 8
[12 empty] | 2017-08-12 | 8
[12 empty] | 2017-08-13 | 8
[12 empty] | 2017-08-14 | 8
[12 empty] | 2017-08-15 | 8
[12 empty] | 2017-08-16 | 8
[12 empty] | 2017-08-17 | 8
[12 empty] | 2017-08-18 | 8
[12 empty] | 2017-08-19 | 8
[12 empty] | 2017-08-20 | 8
[12 empty] | 2017-08-21 | 8
[12 empty] | 2017-08-22 | 8
[12 empty] | 2017-08-23 | 8
[12 empty] | 2017-08-24 | 8
[12 empty] | 2017-08-25 | 8
[12 empty] | 2017-08-26 | 8
[12 empty] | 2017-08-27 | 8
[12 empty] | 2017-08-28 | 8
[12 empty] | 2017-08-29 | 8
[12 empty] | 2017-08-30 | 8
[12 empty] | 2017-08-31 | 8
[12 empty] | 2017-09-01 | 8
[12 empty] | 2017-09-02 | 8
[12 empty] | 2017-09-03 | 8
[12 empty] | 2017-09-04 | 8
[12 empty] | 2017-09-05 | 8
[12 empty] | 2017-09-06 | 8
[12 empty] | 2017-09-07 | 8
[12 empty] | 2017-09-08 | 8
[12 empty] | 2017-09-09 | 8
[12 empty] | 2017-09-10 | 18
[12 empty] | 2017-09-11 | 18
[12 empty] | 2017-09-12 | 18
[12 empty] | 2017-09-13 | 18
[12 empty] | 2017-09-14 | 18
[12 empty] | 2017-09-15 | 18
[12 empty] | 2017-09-16 | 18
[12 empty] | 2017-09-17 | 18
[12 empty] | 2017-09-18 | 18
[12 empty] | 2017-09-19 | 18
[12 empty] | 2017-09-20 | 18
[12 empty] | 2017-09-21 | 18
[12 empty] | 2017-09-22 | 18
[12 empty] | 2017-09-23 | 18
[12 empty] | 2017-09-24 | 18
[12 empty] | 2017-09-25 | 18
[12 empty] | 2017-09-26 | 18
[12 empty] | 2017-09-27 | 18
[12 empty] | 2017-09-28 | 18
[12 empty] | 2017-09-29 | 18
[12 empty] | 2017-09-30 | 18
[12 empty] | 2017-10-01 | 18
[12 empty] | 2017-10-02 | 18
[12 empty] | 2017-10-03 | 18
[12 empty] | 2017-10-04 | 18
[12 empty] | 2017-10-05 | 18
[12 empty] | 2017-10-06 | 18
[12 empty] | 2017-10-07 | 18
[12 empty] | 2017-10-08 | 18
[12 empty] | 2017-10-09 | 18
[12 empty] | 2017-10-10 | 18
[12 empty] | 2017-10-11 | 18
[12 empty] | 2017-10-12 | 18
[12 empty] | 2017-10-13 | 18
[12 empty] | 2017-10-14 | 18
[12 empty] | 2017-10-15 | 18
[12 empty] | 2017-10-16 | 18
[12 empty] | 2017-10-17 | 18
[12 empty] | 2017-10-18 | 18
[12 empty] | 2017-10-19 | 18
[12 empty] | 2017-10-20 | 18
[12 empty] | 2017-10-21 | 18
[12 empty] | 2017-10-22 | 18
[12 empty] | 2017-10-23 | 18
[12 empty] | 2017-10-24 | 18
[12 empty] | 2017-10-25 | 18
[12 empty] | 2017-10-26 | 18
[12 empty] | 2017-10-27 | 18
[12 empty] | 2017-10-28 | 18
[12 empty] | 2017-10-29 | 18
[12 empty] | 2017-10-30 | 18
[12 empty] | 2017-10-31 | 18
[12 empty] | 2017-11-01 | 18
[12 empty] | 2017-11-02 | 18
[12 empty] | 2017-11-03 | 18
[12 empty] | 2017-11-04 | 18
[12 empty] | 2017-11-05 | 18
[12 empty] | 2017-11-06 | 18
[12 empty] | 2017-11-07 | 18
[12 empty] | 2017-11-08 | 18
[12 empty] | 2017-11-09 | 18
[12 empty] | 2017-11-10 | 18
[12 empty] | 2017-11-11 | 18
[12 empty] | 2017-11-12 | 18
[12 empty] | 2017-11-13 | 18
[12 empty] | 2017-11-14 | 20
[12 empty] | 2017-11-15 | 20
[12 empty] | 2017-11-16 | 20
[12 empty] | 2017-11-17 | 20
[12 empty] | 2017-11-18 | 20
[12 empty] | 2017-11-19 | 20
[12 empty] | 2017-11-20 | 20
[12 empty] | 2017-11-21 | 20
[12 empty] | 2017-11-22 | 21
[12 empty] | 2017-11-23 | 22
[12 empty] | 2017-11-24 | 22
[12 empty] | 2017-11-25 | 22
[12 empty] | 2017-11-26 | 22
[12 empty] | 2017-11-27 | 22
[12 empty] | 2017-11-28 | 24
[12 empty] | 2017-11-29 | 24
[12 empty] | 2017-11-30 | 24
[12 empty] | 2017-12-01 | 24
[12 empty] | 2017-12-02 | 24
[12 empty] | 2017-12-03 | 25
[12 empty] | 2017-12-04 | 25
[12 empty] | 2017-12-05 | 25
[12 empty] | 2017-12-06 | 25
[12 empty] | 2017-12-07 | 25
[12 empty] | 2017-12-08 | 25
[12 empty] | 2017-12-09 | 25
[12 empty] | 2017-12-10 | 25
[12 empty] | 2017-12-11 | 25
[12 empty] | 2017-12-12 | 25
[12 empty] | 2017-12-13 | 25
[12 empty] | 2017-12-14 | 25
[12 empty] | 2017-12-15 | 25
[12 empty] | 2017-12-16 | 25
[12 empty] | 2017-12-17 | 25
[12 empty] | 2017-12-18 | 25
[12 empty] | 2017-12-19 | 25
[12 empty] | 2017-12-20 | 27
[12 empty] | 2017-12-21 | 27
[12 empty] | 2017-12-22 | 27
[12 empty] | 2017-12-23 | 27
[12 empty] | 2017-12-24 | 27
[12 empty] | 2017-12-25 | 27
[12 empty] | 2017-12-26 | 28
[12 empty] | 2017-12-27 | 29
[12 empty] | 2017-12-28 | 29
[12 empty] | 2017-12-29 | 29
[12 empty] | 2017-12-30 | 29
[12 empty] | 2017-12-31 | 29
[12 empty] | 2018-01-01 | 29
[12 empty] | 2018-01-02 | 29
[12 empty] | 2018-01-03 | 29
[12 empty] | 2018-01-04 | 29
[12 empty] | 2018-01-05 | 29
[12 empty] | 2018-01-06 | 29
[12 empty] | 2018-01-07 | 29
[12 empty] | 2018-01-08 | 29
[12 empty] | 2018-01-09 | 29
[12 empty] | 2018-01-10 | 29
[12 empty] | 2018-01-11 | 29
[12 empty] | 2018-01-12 | 29
[12 empty] | 2018-01-13 | 29
[12 empty] | 2018-01-14 | 29
[12 empty] | 2018-01-15 | 30
[12 empty] | 2018-01-16 | 30
[12 empty] | 2018-01-17 | 30
[12 empty] | 2018-01-18 | 30
[12 empty] | 2018-01-19 | 30
[12 empty] | 2018-01-20 | 30
[12 empty] | 2018-01-21 | 30
[12 empty] | 2018-01-22 | 30
[12 empty] | 2018-01-23 | 31
[12 empty] | 2018-01-24 | 31
[12 empty] | 2018-01-25 | 32
[12 empty] | 2018-01-26 | 32
[12 empty] | 2018-01-27 | 32
[12 empty] | 2018-01-28 | 32
[12 empty] | 2018-01-29 | 32
[12 empty] | 2018-01-30 | 32
[12 empty] | 2018-01-31 | 32
[12 empty] | 2018-02-01 | 32
[12 empty] | 2018-02-02 | 32
[12 empty] | 2018-02-03 | 32
[12 empty] | 2018-02-04 | 32
[12 empty] | 2018-02-05 | 32
[12 empty] | 2018-02-06 | 32
[12 empty] | 2018-02-07 | 33
[12 empty] | 2018-02-08 | 33
[12 empty] | 2018-02-09 | 33
[12 empty] | 2018-02-10 | 33
[12 empty] | 2018-02-11 | 33
[12 empty] | 2018-02-12 | 33
[12 empty] | 2018-02-13 | 33
[12 empty] | 2018-02-14 | 33
[12 empty] | 2018-02-15 | 33
[12 empty] | 2018-02-16 | 33
[12 empty] | 2018-02-17 | 33
[12 empty] | 2018-02-18 | 33
[12 empty] | 2018-02-19 | 33
[12 empty] | 2018-02-20 | 33
[12 empty] | 2018-02-21 | 33
[12 empty] | 2018-02-22 | 33
[12 empty] | 2018-02-23 | 33
[12 empty] | 2018-02-24 | 33
[12 empty] | 2018-02-25 | 33
[12 empty] | 2018-02-26 | 33
[12 empty] | 2018-02-27 | 36
[12 empty] | 2018-02-28 | 36
[12 empty] | 2018-03-01 | 36
[12 empty] | 2018-03-02 | 36
[12 empty] | 2018-03-03 | 36
[12 empty] | 2018-03-04 | 36
[12 empty] | 2018-03-05 | 36
[12 empty] | 2018-03-06 | 36
[12 empty] | 2018-03-07 | 36
[12 empty] | 2018-03-08 | 37
[12 empty] | 2018-03-09 | 37
[12 empty] | 2018-03-10 | 37
[12 empty] | 2018-03-11 | 37
[12 empty] | 2018-03-12 | 37
[12 empty] | 2018-03-13 | 37
[12 empty] | 2018-03-14 | 37
[12 empty] | 2018-03-15 | 37
[12 empty] | 2018-03-16 | 37
[12 empty] | 2018-03-17 | 37
[12 empty] | 2018-03-18 | 37
[12 empty] | 2018-03-19 | 37
[12 empty] | 2018-03-20 | 37
[12 empty] | 2018-03-21 | 37
[12 empty] | 2018-03-22 | 37
[12 empty] | 2018-03-23 | 37
[12 empty] | 2018-03-24 | 37
[12 empty] | 2018-03-25 | 37
[12 empty] | 2018-03-26 | 37
[12 empty] | 2018-03-27 | 37
[12 empty] | 2018-03-28 | 37
[12 empty] | 2018-03-29 | 37
[12 empty] | 2018-03-30 | 37
[12 empty] | 2018-03-31 | 37
[12 empty] | 2018-04-01 | 37
[12 empty] | 2018-04-02 | 37
[12 empty] | 2018-04-03 | 37
[12 empty] | 2018-04-04 | 37
[12 empty] | 2018-04-05 | 37
[12 empty] | 2018-04-06 | 37
[12 empty] | 2018-04-07 | 37
[12 empty] | 2018-04-08 | 37
[12 empty] | 2018-04-09 | 37
[12 empty] | 2018-04-10 | 37
[12 empty] | 2018-04-11 | 37
[12 empty] | 2018-04-12 | 37
[12 empty] | 2018-04-13 | 37
[12 empty] | 2018-04-14 | 37
[12 empty] | 2018-04-15 | 37
[12 empty] | 2018-04-16 | 37
[12 empty] | 2018-04-17 | 37
[12 empty] | 2018-04-18 | 37
[12 empty] | 2018-04-19 | 37
[12 empty] | 2018-04-20 | 37
[12 empty] | 2018-04-21 | 37
[12 empty] | 2018-04-22 | 37
[12 empty] | 2018-04-23 | 37
[12 empty] | 2018-04-24 | 37
[12 empty] | 2018-04-25 | 37
[12 empty] | 2018-04-26 | 37
[12 empty] | 2018-04-27 | 37
[12 empty] | 2018-04-28 | 37
[12 empty] | 2018-04-29 | 37
[12 empty] | 2018-04-30 | 37
[12 empty] | 2018-05-01 | 37
[12 empty] | 2018-05-02 | 37
[12 empty] | 2018-05-03 | 37
[12 empty] | 2018-05-04 | 37
[12 empty] | 2018-05-05 | 37
[12 empty] | 2018-05-06 | 37
[12 empty] | 2018-05-07 | 37
[12 empty] | 2018-05-08 | 37
[12 empty] | 2018-05-09 | 37
[12 empty] | 2018-05-10 | 37
[12 empty] | 2018-05-11 | 37
[12 empty] | 2018-05-12 | 37
[12 empty] | 2018-05-13 | 37
[12 empty] | 2018-05-14 | 37
[12 empty] | 2018-05-15 | 37
[12 empty] | 2018-05-16 | 37
[12 empty] | 2018-05-17 | 37
[12 empty] | 2018-05-18 | 37
[12 empty] | 2018-05-19 | 37
[12 empty] | 2018-05-20 | 37
[12 empty] | 2018-05-21 | 37
[12 empty] | 2018-05-22 | 37
[12 empty] | 2018-05-23 | 37
[12 empty] | 2018-05-24 | 37
[12 empty] | 2018-05-25 | 37
[12 empty] | 2018-05-26 | 37
[12 empty] | 2018-05-27 | 37
[12 empty] | 2018-05-28 | 37
[12 empty] | 2018-05-29 | 37
[12 empty] | 2018-05-30 | 37
[12 empty] | 2018-05-31 | 37
[12 empty] | 2018-06-01 | 37
[12 empty] | 2018-06-02 | 37
[12 empty] | 2018-06-03 | 37
[12 empty] | 2018-06-04 | 37
[12 empty] | 2018-06-05 | 37
[12 empty] | 2018-06-06 | 37
[12 empty] | 2018-06-07 | 37
[12 empty] | 2018-06-08 | 37
[12 empty] | 2018-06-09 | 37
[12 empty] | 2018-06-10 | 37
[12 empty] | 2018-06-11 | 37
[12 empty] | 2018-06-12 | 37
[12 empty] | 2018-06-13 | 37
[12 empty] | 2018-06-14 | 37
[12 empty] | 2018-06-15 | 37
[12 empty] | 2018-06-16 | 37
[12 empty] | 2018-06-17 | 37
[12 empty] | 2018-06-18 | 37
[12 empty] | 2018-06-19 | 37
[12 empty] | 2018-06-20 | 37
[12 empty] | 2018-06-21 | 37
[12 empty] | 2018-06-22 | 37
[12 empty] | 2018-06-23 | 37
[12 empty] | 2018-06-24 | 37
[12 empty] | 2018-06-25 | 37
[12 empty] | 2018-06-26 | 37
[12 empty] | 2018-06-27 | 37
[12 empty] | 2018-06-28 | 37
[12 empty] | 2018-06-29 | 37
[12 empty] | 2018-06-30 | 37

## Workflows
Link
Account | Flow |  |  |  | Krrish Dev. | Classification |  | Threshold Config | Parsing | [6 empty] | % in Training data |  |  | Recall on test set |  | Full Auto Error on test set
| Phase | Name | Krrish Name | Type |  | Status | Model |  | Entity | Atom | Configuration | Note | Status | Description | Production Date | Total | External | Internal | TH = 0.5 | Lower TH | TH = 0.5 | Higher TH | MRFPR
Globe | Prod. - Activated | Rated events extraction | Rated Events Extraction | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.5, 0.3 | MSISDN (M) | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact","requestor's phone", "contact's phone", "requestor's contact"], first_digit = 9) |  | configured | User/s usage report (data/voice/SMS) | 2017-08-06 | 4.91% | 5.16% | - | 85% | 85.19% | 11% | 11% | 1-8 | 12.5%
[9 empty] | DATE_FROM, DATE_TO | Date-Range | DateRangeExtractor(from_range_name = 'DATE_FROM', to_range_name = 'DATE_TO', time_zone = 'Asia/Manila') |  | configured
[9 empty] | VOICE | Regex | RegexExtractor(extraction_regex = r"""voice¦call?s""" , indicator = True) |  | configured
[9 empty] | SMS | Regex | RegexExtractor(extraction_regex = r"""sms¦text¦txt¦msg¦messag?e?s""" , indicator = True) |  | configured
[9 empty] | DATA | Regex | RegexExtractor(extraction_regex = r"""data¦internet""" , indicator = True) |  | configured
[9 empty] | ROAMING_IND | Regex | RegexExtractor(extraction_regex = r"""\\sroaming¦\\sroam\\s""" , indicator = True) |  | configured
Globe | Prod. - Activated | LTP no load received | LTP_NO_LOAD_RECEIVE | Ext. |  |  |  | 0.7,0.15 | MSISDN (M) | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact"] ,first_digit = 9) |  | configured | LTP stands for Load Tipid Plan. A Hybrid prepaid-postpaid program. Training issue. RPL flow where subscriber did not received monthly recharge. This is a training issue due to CSR did not validate completely why subs did not receive load and upon checking. It is a valid scenario where subs is still in collection. | 2017-08-06 | 2.59% | 2.72% | - | 88% | 88% | 5% | 5% | 1-9 | 11.11%
[9 empty] | SEEDING_DATE | Regex | RegexExtractor(extraction_regex = r"""((seed¦sedd¦seeed)(.{1,50})(\\b((?:[1-9]¦0[1-9]¦[1-2][0-9]¦3[0-1]))(\\s¦$)))¦((\\b1st)¦(21st)¦(31st)¦(\\b2nd)¦(22nd)¦(10th)¦(11th)¦(12th)¦(13th)¦(\\b3rd)¦(23rd)¦([1-2]?(0¦[4-9])th))""" , integer_indicator = True, length_limit = 2, default_value = datetime.datetime.now().strftime('%d')) |  | configured
Globe | Prod. - Activated | ASMM variance found base | MEDIATION_REPORT | Ext. |  |  |  | 0.5,0.5 | FILE_IDENTIFIER (M) | Globe_ASMM | Globe_ASMMVariance_FileIdExtractor() | Comes in an attached .zip file | configured | ASMM Variance found base. Summary contains "Variance found base on ASMM VS TC base on daily analysis and A&C balance report“ | 2017-08-06 | 0.92% | 0.97% | - | 100% | 100% | 0% | 0% | 0-0 | 0%
Globe | Prod. - Activated | Hold activity cancellation | Hold Activity Cancellation | Ext. |  |  |  | 0.4,0.2 | ORDER_ID | Regex | RegexExtractor(extraction_regex = r"""(\\D\\d{9}\\d?)([a]¦[A])""", integer_indicator = True) |  | configured | Order cancellation in Hold activity. Script is being used to enable cancel order button | 2017-08-06 | 0.76% | 0.8% | - | 40% | 84.71% | 3% | 3% | 5-32 | 15.62%
[9 empty] | MSISDN | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact","requestor's phone", "contact's phone", "requestor's contact"], first_digit = 9) |  | configured
Globe | Prod. - Activated | Duo Alignment | Duo Alignment | Ext. |  |  |  | 0.5,0.25 | Multiple | Globe_Duoalignment | Default Values |  | configured |  | 2017-12-20 | 1.65% | 1.73% | - |  |  |  |  | 0-1 | 0%
Globe | Prod. - Activated | Reconnection Checking | Reconnection | Ext. |  |  |  | 0.7, 0.25 | MSISDN | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact","requestor's phone", "contact's phone", "requestor's contact"], first_digit = 9) |  | configured |  | 2017-09-10 | 1.32% | 1.38% | - |  |  |  |  | 11-25 | 44%
[9 empty] | TICKET_DATE | Create Date | CreateDateExtractor(timezone_offset = 13)
Globe | Prod. - Activated | Bulk Barring | Bulk Barring | Ext. |  |  |  | 0.5,0.4 | DATA, File | Globe_Bulkbarring | GlobeBulkbarringExtractor() | May come in an attached .zip file | configured |  | 2017-12-20
Globe | Dev. | Misaligned Component - MRF |  | Ext. |  |  |  |  | MSISDN
[9 empty] | Cycle_Month |  |  | if date range - last date
[9 empty] | Cycle_Year |  |  | usually prefaced by "Occurrence Date"
Globe | Dev. - Testing | SRM Extraction | SRM Extraction | Ext. |  |  |  | 0.5,0.3 | Multiple | GlobeSrmExtractionExtractor | GlobeSrmExtractionExtractor() |  | configured
[9 empty] | Request_Type | Regex | RegexExtractor("entity_name"= "Request_Type", "extraction_regex"= "(?<=Request\\sType(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Resource_Type | Regex | RegexExtractor("entity_name"= "Resource_Type", "extraction_regex"= "(?<=Resource\\sType(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Resource | Regex | RegexExtractor("entity_name"= "Resource", "extraction_regex"= "(?<=Resource)(:?)(\\s?)\\d.*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Status | Regex | RegexExtractor("entity_name"= "Status", "extraction_regex"= "(?<=Status(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Category | Regex | RegexExtractor("entity_name"= "Category", "extraction_regex"= "(?<=Category(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Area_Name | Regex | RegexExtractor("entity_name"= "Area_Name", "extraction_regex"= "(?<=Area\\sName(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Post_Pre | Regex | RegexExtractor("entity_name"= "Post_Pre", "extraction_regex"= "(?<=Post\\s\/\\sPre(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Date_From | Regex | RegexExtractor("entity_name"= "Date_From", "extraction_regex"= "(?<=Date\\sFrom(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
[9 empty] | Date_To | Regex | RegexExtractor("entity_name"= "Date_To", "extraction_regex"= "(?<=Date\\sTo(?!\\n)).*", "remove_char"=":", "replace_char"= ["^\\s",""]) |  | configured
Sprint | Prod. - Activated | Complete order | complete order | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.8,0.5 | Order_Number (M) | Regex | RegexExtractor(extraction_regex =r"""((COM\\d)¦(DM\\d{2}))-?O-?\\d{6}\\d?\\d?""", remove_char = "-", upper_case = True) |  | configured | Completing orders that have gotten stuck in an incomplete status | 2017-08-06 | 2.03% | 4.07% | - | 92% | 92% | 9% | 4% | 10-37 | 27.03%
Sprint | Prod. - Activated | MPD date incorrect | Sprint_INCORRECT MPD DATE CORRECTED | Ext. |  |  |  | 0.7,0.5 | BAN (M) | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)\d{9}(\\b¦\\D)""",exclusion_list = ["Secondary", "secondary"],exclusion_offset=30, unique_indicator = False, integer_indicator = True) | May appear in the Summary field, Take only Primary number | configured | Resetting monthly payment dates on suspended prepaid accounts | 2017-08-06 | 0.37% | 0.74% | - | 67% | 67% | 12% | 2% | 6-17 | 35.29%
Sprint | Prod. - Activated | Re-push Order | Repush Order Line | Ext. |  |  |  | 0.5 0.5 | Order_Number (M) | Sprint_Repush |  |  | configured |  | 2017-09-10 | 0.86% | 1.73% | - | 100% | 100% | 0% | 0% | 0-0 | 0%
Sprint | Prod. - Activated | Edit Memo | Sprint_Mask Memo | Ext. |  |  |  | 0.6,0.2 | BAN | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)\d{9}(\\b¦\\D)""", inclusion_list=["BAN","BAN:"], inclusion_offset = 20, unique_indicator = False, integer_indicator = True) |  | configured |  | 2017-09-10 | 1.15% | 2.31% | - | 92% | 100% | 6% | 4% | 2-11 | 18.18%
[9 empty] | PTN | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact","Office Phone","Mobile Phone","Number"]) |  | configured
[9 empty] | Memo_ID | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)I?\\d?\\d{10}(\\b¦\\D)""",inclusion_list = ["Memo ID"], inclusion_offset = 20, remove_char = " ", upper_case = True) |  | configured
[9 empty] | Memo_Details_to_Remove | Regex | RegexExtractor(extraction_regex =r"""Memo\\s{,3}Details\\s{,3}to\\s{,3}Remove:(.+)\\n""",remove_char = "(m¦M)emo\\s{,3}(d¦D)etails\\s{,3}(T¦t)o\\s{,3}(r¦R)emove:") |  | configured
Sprint | Prod. - Activated | Clear PI PTN | Sprint Clear PI PTN | Ext. |  |  |  | 0.4,0.1 | PTN | Phone Number | PhoneNumberExtractor(exclusion_list = ["requestor phone", "contact phone", "requestor contact","Office Phone","Mobile Phone","Number"]) |  | configured |  | 2017-11-28
Sprint | Prod. - Activated | Cancel Order | Sprint Cancel Order | Ext. |  |  |  | 0.6, 0.3 | Order_Number (M) | Regex | RegexExtractor(extraction_regex =r"""((COM\\d)¦(DM\\d{2}))-?O-?\\d{6}\\d?\\d?""", remove_char = "-", upper_case = True) |  | configured |  | 2017-11-14
Sprint | Prod. - Activated | CSM-RPL Production Sanity | CSM-RPL Production Sanity | Int. |  | Trained Desc - 0.1, Summ - 0.9 |  | 0.5,0.5 | PTN (M) | Phone Number | PhoneNumberExtractor("icnlusion_list" = ["PTN"], inclusion_offset = 30) | MSISDN | configured |  | 2017-08-06 | Non-UTS, Received by e-mail |  |  | 100% | 100% | 0% | 0% | 0-0 | 0%
Sprint | Prod. - Activated | Threshold_Break | Advance MRC Threshold Break | Int. |  |  |  | 0.9,0.5 | TZ (M) | Regex | RegexExtractor(extraction_regex =r"""(TZ¦Time Zone)(\\s{,5}?)([\\d]+)""", remove_char = "[^0-9]") |  | configured |  | 2017-08-06 | 0.25% | - | 0.49% | 100% | 100% | 0% | 0% | 0-0 | 0%
Sprint | Prod. - Activated | First RC | SPRINT Prepaid First RC | Int. |  |  |  | 0.5,0.3 | BAN_SUBSCRIBER | Regex |  |  | configured |  | 2017-09-10 | Non-UTS, Received by e-mail |  |  | 100% | 100% | 0% | 0% | 0-0 | 0%
Sprint | Prod. - Activated | Zero RC | SPRINT Prepaid Zero RC | Int. |  |  |  | 0.5,0.3 | BAN_SUBSCRIBER | Regex |  |  | configured |  | 2017-11-14
Sprint | Prod. - Activated | Linkage Wrapper | SPRINT Linkage Wrapper | Int. |  |  |  | 0.6, 0.5 | TZ (M) | Regex | RegexExtractor(extraction_regex =r"""(TZ¦Time Zone)(\\s{,5}?)([\\d]+)""", remove_char = "[^0-9]") |  | configured |  | 2017-11-28
XL Axiata | Prod. - Activated | Age Out | Age_Out | Ext. |  | Trained Desc - 0.4, Summ - 0.6 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.7,0.3 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000) |  | configured | Customer/frontline activate subscriber, then they request to Billing Helpdesk - change status from Aging to Assigned | 2017-09-10 | 11.75% | 12.41% | - | 100% | 100% | 3% |  | 1-5 | 20%
XL Axiata | Prod. - Activated | Customer Booking | Customer_Booking | Ext. |  |  |  | 0.6,0.4 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000) |  | configured | Customer/frontline activate subscriber, then they request to Billing Helpdesk - change status from Reserved Prio to Reserved VRM | 2017-09-10 | 0.95% | 1.007% | - | 95% | 95% | 10% |  | 0-0 | 0%
XL Axiata | Prod. - Activated | Unsync VRM Active/Cancel | Unsync CM CRM | Ext. |  |  |  | 0.5,0.2 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000) |  | configured | Customer/frontline want to checking subscriber in CRM Smartclient but it’s was not sync in status (Cancel/Active) with CM DB/VRM Tool | 2017-09-10 | Non-UTS, Received by e-mail |  |  | 79.17% | 87.5% | 0% | 0% | 2-10
XL Axiata | Dev. - Testing | Wrong Charging | Wrong Charging | Ext. |  |  |  | 0.8,0.5 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000) |  | configured | Customer/frontline complaint if subscriber got wrong charge based on call detail at specific time frame when compared with benefit from Active Price Plan / AO Offer. |  | 16.62% | 17.56% | - | 96% | 96% | 3.346% |  | 11-121 | 9.091%
XL Axiata | Prod. - Deactivated | Quota not update | Quota NUD | Ext. |  |  |  | 0.7,0.5 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000) |  | configured | Customer/frontline complaint if subscriber can’t check quota based on benefit of Active AO Offer from UMB/Network *123# |  | 24.47% | 25.85% | - | 100% | 100% | 3% | 0.5464% | 9-67 | 13.43%
[9 empty] | ISSUE_DATE | DateTimeExtractor | DateTimeExtractor(entity_name= "ISSUE_DATE", inclusion_list: =["cust sudah rec","aktivasi","activation date","waktu","tf","time frame","Time Frame","Time frame","tanggal","t.frime","kejadian"], inclusion_offset:=40, format_to_extract= 2, unique_indicator = false) |  | configured |  | 2018-01-25
[9 empty] | SOCCD | XlcomSocDictExtractor | XlcomSocDictExtractor(entity_name="SOCCD") |  | configured
XL Axiata | Labeling | Recurring Failed
XL Axiata | Prod. - Activated | OC Insufficient Balance | OC Insufficient Balance | Ext. |  |  |  | 0.5,0.4 | MSISDN (M) | Xlcom_Msisdn | XlcomMsisdnExtractor(entity_name:="MSISDN", inclusion_list= ["Description:"],inclusion_offset= 4000, exclusion_list=["VLR address"]) |  | configured |  | 2017-11-22 | 4.11% | 4.34% | -
Cricket | Prod. - Activated | Auto Pay Issue | Un-enroll AutoPay | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 250 trees | 0.5,0.2 | BAN (M) | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)\d{9}(\\b¦\\D)""", unique_indicator = True, integer_indicator = True) |  | configured |  | 2017-09-10 | 2.15% | 4.23% | - | 76.47% | 98.53% | 8% | 8% | 8-12 | 66.67%
Cricket | Prod. - Activated | Cricket Cancel Port In Eligibility Check | Cricket Cancel Port In Eligibility Check | Ext. |  |  |  | 0.5,0.2 | CTN | CricketEligibilityCheck |  |  | configured |  | 2018-02-27 | 2.907% | 5.72% | -
Cricket | Descoped | Cancel Port | Cancel Port In/Out | Ext. |  |  |  | 0.65,0.5 | PTN | Phone Number | PhoneNumberExtractor() |  | configured |  |  | 18.48% | 36.38% | - | 96.91% | 96.91% | 3.442% | 1.916%
[9 empty] | BAN | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)\d{9}(\\b¦\\D)""", unique_indicator = True, integer_indicator = True) |  | configured
Cricket | Descoped | Complete Port | Complete Port In/Out | Ext. |  |  |  | 0.5,0.2 | PTN | Phone Number | PhoneNumberExtractor() |  | configured |  | 2017-09-10 | 1.83% | 3.6% | - | 19.61% | 66.67% | 16.67% | 16.67% | 33-59 | 55.93%
Cricket | Descoped | Change CTN |  | Ext. |  |  |  |  | CTN | [6 empty] | 1.36% | 2.69% | -
Cricket | Descoped | Complete Order |  | Ext. |  |  |  |  | Order ID | Regex | RegexExtractor(extraction_regex =r"""(ORD)-?O-?\\d{6}\\d?\\d?""", remove_char = "-", upper_case = True) |  | configured |  |  | 0.56% | 1.09% | -
[9 empty] | PTN | Phone Number | PhoneNumberExtractor() |  | configured
[9 empty] | BAN | Regex | RegexExtractor(extraction_regex =r"""(^¦\\D)\d{9}(\\b¦\\D)""", unique_indicator = True, integer_indicator = True) |  | configured
Cricket | Descoped | Resume Subscriber |  | Ext. |  |  |  |  | PTN | [6 empty] | 0.75% | 1.47% | -
BAN
Cricket | Descoped | Unable access data |  | Ext. | [11 empty] | 1.17% | 2.31% | -
Cricket | Prod. - Activated | BLDECMPRECON Issue | BLDECMPRECON | Int. |  | Trained Desc - 0.4, Summ - 0.6 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.4,0.3 | - |  |  |  | configured |  | 2017-09-10 | 1.15% | - | 2.34% | 97% | 100% | 0% | 0% | 0-0 | 0%
Cricket | Prod. - Activated | Rejects in Confirmation | Rejects in Confirmation | Int. |  |  |  | 0.5, 0.15 | - |  |  |  | configured |  | 2018-01-23 | 0.2064% | - | 0.42%
Cricket | Prod. - Activated | Portal Orders Payment Statistics for Last Hour | Portal Orders Payment Statistics for Last Hour | Int. |  |  |  | 0.6, 0.3 | - |  |  |  | configured |  | 2018-02-07
Cricket | Prod. - Activated | CSM Pending Payments From CSPYMREPRCSS | CSM Pending Payments From CSPYMREPRCSS | Int. |  |  |  | 0.5, 0.4 | - |  |  |  | configured |  | 2018-02-27
Cricket | Dev. - Testing | Rejects in Billing | Rejects in billing | Int. |  |  |  | 0.5, 0.4 | -
Cricket | Prod. - Activated | BLDECOMSUBTX | BLDECOMSUBTX | Int. |  |  |  | 0.25, 0.2 | - | [5 empty] | 2018-02-27
USCC | Prod. - Activated | Cancel FA | Cancel FA | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.6,0.35 | Customer ID | Regex | RegexExtractor(entity_name="Customer ID", "inclusion_list"= ["Customer id"],"inclusion_offset":=20, "exclusion_list": = ["\\bFA\\b","FA_ID","FA ID","Cancel FA","cancel the following FA","please close FA","FA Cancel"], "exclusion_offset"=20, "extraction_regex"= (^¦\\D)\\d{9}(\\b¦\\D), "unique_indicator": = True, "integer_indicator": = True) |  | configured |  | 2017-11-23 | 15.75%
[9 empty] | FA_ID | Regex | RegexExtractor("entity_name"="\\bFA\\b", "FA_ID", "inclusion_list": = ["FA_ID","FA ID","Cancel FA","cancel the following FA","please close FA","FA Cancel"], "inclusion_offset"=80, "exclusion_list"= ["Customer id"],"exclusion_offset":=20, "extraction_regex"= "(^¦\\D)\\d{9}(\\b¦\\D)", "integer_indicator"= True) |  | configured
USCC | Prod. - Activated | Prepaid Customer | PREPAID CUSTOMER WITHOUT SERVICE | Ext. |  |  |  | 0.6,0.3 | Customer_ID | Regex | RegexExtractor(entity_name="Customer ID", "inclusion_list"= ["Customer id"],"inclusion_offset":=20, "extraction_regex"= (^¦\\D)\\d{9}(\\b¦\\D), "unique_indicator": = True, "integer_indicator": = True) |  | configured |  | 2018-11-29 | 5.74%
[9 empty] | MDN | Phone Number | PhoneNumberExtractor(inclusion_list = ["MDN"]) |  | configured
USCC | Prod. - Activated | Registration Issue | Prepaid Registration | Ext. |  |  |  | 0.5,0.2 | Customer ID | Regex | RegexExtractor(entity_name="Customer ID", "inclusion_list"= ["Customer id"],"inclusion_offset":=20, "extraction_regex"= (^¦\\D)\\d{9}(\\b¦\\D), "unique_indicator": = True, "integer_indicator": = True) |  | configured |  | 2017-12-03 | 3.47%
[9 empty] | Attachment | UsccPrepaidRegistrationExtractor | UsccPrepaidRegistrationExtractor(entit_name="Attachment")
USCC | Dev. - Testing | ESN Blacklist | USCC ESN | Ext. |  |  |  | 0.55,0.2 | ESN_MEID | Regex | RegexExtractor(entity_name="ESN/MEID", "inclusion_list"= ["esn","meid","esn/meid"],"inclusion_offset":=20, "extraction_regex"= (^¦\\D)\\d?\\d{17}(\\b¦\\D), "integer_indicator": = True) |  | configured |  |  | 1.02%
USCC | Dev. - Testing | Billing Rejects | Billing Rejects | Both |  |  |  | 0.8,0.3 | Defect ID | Regex | 1. RegexExtractor(entity_name="Defect ID", "inclusion_list"= ["BILLING_CYCLE","BILL_CYCLE","defect","hold"],"inclusion_offset":=100, "extraction_regex"= \\D\\d?\\d?\\d{5}(\\D¦$), "integer_indicator": = True) 2. RegexExtractor(entity_name="Defect ID", "extraction_regex"= (D(\\#?))\\d?\\d?\\d{5}(\\D¦$), "integer_indicator": = True) |  | configured |  |  | 4.21%
USCC | Prod. - Activated | PULL BILLS AFP | PULL BILLS AFP | Ext. |  |  |  | 0.5, 0.4 | AFP_NAME | Regex | RegexExtractor(entity_name="AFP_NAME", "extraction_regex"= "DD.USC.\\d{4}.\\d{2}.\\d{4}.\\*.afp") |  |  |  | 2018-03-08
USCC | Dev. | Overage Notification | Overage Notification | Ext. |  |  |  | 0.6,0.1
USCC | Dev. | RC Drop | RC Drop | Int. |  |  |  | 0.5, 0.4
Bell Canada | Dev. | ADD User |  | Ext. |  | Default | Default | [8 empty] | 36.6% | 62.5% | -
Bell Canada | Dev. | DELETE User |  | Ext. | [11 empty] | 36.6% | 62.5% | -
Bell Canada | Dev. | UPDATE User |  | Ext. | [11 empty] | 36.6% | 62.5% | -
Airtel | Prod. - Activated | Order Not Generated | Order Not Generated | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.6, 0.3 | Mobile_Number | Regex | RegexExtractor: "entity_name": "Mobile_No", "extraction_regex":"((?<=\\D)¦(?<=\\b)¦(?<=''))[7-9](\\d{9})((?=\\b)¦(?=\\s)¦(?=\\D))", "integer_indicator": true,"replace_char": ["_"," _ "], "exclusion_list": ["sfo"], "exclusion_offset": 20 | No impact of full automation that is FP |  |  | 2018-01-15 | 36.6% | 62.5% | -
[9 empty] | Mobile_Number |  | AirtelPendingForActivationExtractor("entity_name" = ["Mobile_No"])
Airtel | Prod. - Activated | SR and Task Closure | SR and Task closure | Ext. |  |  |  | 0.8,0.5 | SR Number | Regex | RegexExtractor( "entity_name"= "SR Number", "extraction_regex"="(?<=\D)\d{8}(?=(\D¦$))") | No impact of full automation that is FP |  |  | 2017-12-26
[9 empty] | LOB | Regex | ListExtractor( "entity_name"="LOB", "extraction_regex"= (\\bABGB\\b)¦(\\bDTH\\b)¦(\\bMobility\\b)¦(\\bTelemedia\\b)¦(\\bIT\\b), "inclusion_list"=["LOB"], "default_value"=['telemedia'])
Airtel | Prod. - Activated | Pending for Activation | Pending for Activation | Ext. |  |  |  | 0.6,0.3 | Mobile_No | Regex | RegexExtractor: "entity_name": "Mobile_No", "extraction_regex":"((?<=\\D)¦(?<=\\b)¦(?<=''))[7-9](\\d{9})((?=\\b)¦(?=\\s)¦(?=\\D))", "integer_indicator": true, "exclusion_list": ["sfo"], "exclusion_offset": 20 | No impact of full automation that is FP |  |  | 2017-12-27
[9 empty] | Mobile_No | PendingForActivationExtractor | AirtelPendingForActivationExtractor("entity_name" = ["Mobile_No"])
Airtel | Prod. - Activated | NMS Release Scenario | NMS Release Scenario | Ext. |  |  |  | 0.5, 0.2 | From_Number_To_Number | From_Number_To_Number |  | Impact on full automation
Airtel | Dev. - Testing | P2P Request Deletion | P2P Request Deletion | Ext. |  |  |  | 0.5, 0.3 | Mobile_No | Regex | RegexExtractor("entity_name": "Mobile_No", "extraction_regex":"((?<=\\D)¦(?<=\\b)¦(?<=''))[7-9](\\d{9})((?=\\b)¦(?=\\s)¦(?=\\D))", "integer_indicator": true, "exclusion_list": ["regards"], "exclusion_offset": 500)
[9 empty] | Request_ID | Regex | RegexExtractor("entity_name": "Request_ID", "extraction_regex":"((?<=\\D)¦(?<=\\b)¦(?<=''))(\\d{7})((?=\\b)¦(?=\\s)¦(?=\\D))", "integer_indicator": true)
Airtel | Dev. | P2P ID Creation | P2P ID Creation | Ext. |  |  |  | 0.5, 0.3 | Multiple | airtel_p2p_id_creation_extractor
Airtel | Dev. | Barring | Barring | Ext. |  |  |  | 0.5, 0.2
Airtel | Prod. - Activated | Unbarring | Unbarring | Ext. |  |  |  | 0.7, 0.3 | Mobile_Number | Regex |  | Impact on full automation
Airtel | Dev. | Task Closure |  | Ext. |  |  |  |  | Mobile_Number
Tef Argentina | Dev. | Stuck Order | [6 empty] | Order_number
MetroPCS | Labeling | Unknown
Telkomsel | Dev. | Notify Billing |  | Ext. |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 100 trees | 0.5,0.3 | Order_number
MSISDN
Telkomsel | Dev. | Subscriber status check |  | Ext. |  |  |  | 0.7,0.3 | MSISDN
Telkomsel | Dev. | Subscriber refresh / alignment |  | Ext. |  |  |  | 0.5,0.2 | MSISDN
Telkomsel | Dev. | Resume MSISDN - AC status |  | Ext. |  |  |  | 0.5,0.2 | MSISDN
Note on F3: Green - active workflow in production Yellow - active in prod. but disabled Blue - Fully ready for E2E testing
Note on AF3: Manual Recommendation False Positive Rate
Note on P48: PhoneNumberExtractor(added_digits = 3)
Note on P49: PhoneNumberExtractor(added_digits = 3)
Note on P50: PhoneNumberExtractor(added_digits = 3)
Note on P51: PhoneNumberExtractor(added_digits = 3)
Note on P52: PhoneNumberExtractor(added_digits = 3)
Note on P56: PhoneNumberExtractor(added_digits = 3)
Note on G87: Trained as "All"

## Dispatch flows
Account | Flow |  |  |  | Krrish Dev. | Classification |  | Threshold Config |  |  | % in Training data |  |  | Recall on test set |  | Full Auto Error on test set
| Phase | Support Group | Support Group ID | Flow Name |  | Status | Model |  | Description | Production Date | Total | External | Internal | TH = 0.5 | Lower TH | TH = 0.5 | Higher TH
Globe | Prod. - Activated | NBU | SGP000000001133 | Business |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 200 trees | 0.5 |  | 2017-09-10
Globe | Prod. - Activated | EPC | SGP000000001130 | Service Configuration |  |  |  | 0.3 |  | 2017-09-10
Globe | Descoped | Usage | SGP000000001367 | PER Downstream Variance |  |  |  | 0.3 |  | 2017-09-10
Globe | Descoped |  |  | Trending files with zero records |  |  |  | 0.3
Globe | Descoped |  |  | Variance found on CDR |  |  |  | 0.3
Globe | Prod. - Activated |  |  | Rejects |  |  |  | 0.3 |  | 2017-12-15
USCC | Descoped |  |  | Amdocs SEVA |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 200 trees | 0.5
USCC | Prod. - Activated |  |  | Recycle Event issue |  |  |  | 0.6 |  | 2018-01-16
USCC | Descoped |  |  | Accelerate Device Financing |  |  |  | 0.3
USCC | Descoped |  |  | EOM |  |  |  | 0.5
USCC | Prod. - Activated |  |  | AR1JRNLEXT Running Long |  |  |  | 0.4 |  | 2018-01-16
Sprint | Prod. - Activated |  |  | Sprint_API |  | Trained Desc - 0.5, Summ - 0.5 | 1. N gram - 2 2. Chi2 - 20% 3. Random Forest - 200 trees | 0.5 |  | 2018-03-08
Sprint | Prod. - Activated |  |  | Sprint_DRF |  |  |  | 0.5 |  | 2018-03-08
Sprint | Prod. - Activated |  |  | Sprint_MonAdjust |  |  |  | 0.5 |  | 2018-03-08

## Amily PoC Status (hidden)
Globe | [6 empty] | Clustering
Flow | Classification |  |  | Parsing |  |  | Account | Internal/External | Supervised Evaluation | Status
| IBM | SAS | FOSS | IBM | SAS | FOSS | Globe | External | Yes
ASMM Variance found base | [6 empty] | Sprint | Internal | No
Hold Activity Cancellation |  |  |  |  | Evaluate | Code | TKS | External | No
LTP No Load Receive |  |  | ` |  |  |  | TKS | External | Yes - Globe
Misaligned Component - MRF | [6 empty] | TKS | External | Yes - Sprint
PER Downstream Variance | [6 empty] | Metro | External | Yes - Globe
Rated Events Extraction |  |  |  |  | Evaluate |  | Metro | External | Yes - Sprint
Service Configuration | [6 empty] | XL Axiata | External | No
Trending files with zero records
Variance found on CDR
Other | [6 empty] | Deployment feasibility PoC - all 3 tools
Robust deployment feasibility PoC - with or w/o source code on
OCR in python
Sprint | [6 empty] | Gitlab
Flow | Classification |  |  | Parsing
| IBM | SAS | FOSS | IBM | SAS | FOSS
Cancel Subscriber
Complete Order |  |  |  |  | Evaluate
Daily DRF |  |  |  |  | Evaluate | Code
Funds Not Sweeping
MPD date incorrect
Update PTN |  |  |  |  | Evaluate | Code
Other

## Amily PoC Contacts (hidden)
Vendor | Name | Phone Number | E-mail
IBM | Jorge Vulej | 050-9926431 | ITZHAKVULEJ@IBM.COM
IBM | Omer Mizrachi | 058-6485787 | OMERMI@il.ibm.com
SAS | Yoni Barak | 054-6400073 | Jonathanb@miac.com
SAS | Hagay Goldman | 052-6678805 | Hagay.Goldman@sas.com
SAS | Dina Gelfond | 052-8195582 | DinaG@miac.com
FOSS | Yuval Feinstein | 058-5113545 | fyuval@gmail.com